## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US001 | Project setup requirements (Voice Based Patient Call System) | MUST HAVE | VS Code, Extensions, Git | Laeeba Javed | 3- Completed
S2 | S2 | US001 | Working on Frontend and Backend | MUST HAVE | React Native, Expo, MongoDB, NodeJS | Laeeba Javed | 3- Completed
S3 | S3 | US001 | Running both Frontend and Backend together | MUST HAVE | React Native, Expo, MongoDB, NodeJS | Laeeba Javed | 3- Completed
S4 | S4 | US001 | Integrating Project with AI | MUST HAVE | Gemini API | Laeeba Javed | 3- Completed
S5 | S5 | US001 | Runnng and Testing the whole project | MUST HAVE | React Native, Node JS, Expo, MongoDB, Gemini API | Laeeba Javed | 3- Completed

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 2 | Lack of clarity on project requirements | Conducted a team and mentor discussion to define project scope, focusing on patient call workflows and required APIs.
Sprint 1 | Day 4 | Lack of clarity on specific project goals and workflow steps. | Conducted a brainstorming session to outline features, including call scheduling, voice processing integration, and notification triggers.
Sprint 2 | Day 6 | Agile template confusion | Held a mentor-led session to demonstrate how to use Agile boards for tracking tasks like API integration and UI updates in React Native.
Sprint 2 | Day 7 | Difficulty in identifying all potential use cases due to incomplete information. | Researched similar healthcare projects (e.g., Patient request, emergency alerts) to refine functional requirements.
Sprint 2 | Day 9 | Confusion about prioritizing use cases for preparation. | Created a priority matrix using Agile methods to prioritize critical features like patient call routing and appointment notifications.
Sprint 3 | Day 12 | Difficulty in debugging Node.js practice code | Collaborated with team members to resolve issues, ensuring Node.js APIs interacted correctly with MongoDB Atlas.
Sprint 4 | Day 16 | SQL queries taking longer than expected | Revisited MongoDB database design, optimized queries using indexes, and received guidance on query structuring.
Sprint 5 | Day 23 | Challenges integrating voice processing with workflows | Scheduled a debugging session to address React Native voice processing modules and backend API issues in Node.js.

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2024-11-04 | 2024-11-08 | Sahabi,Laeeba,Vishal, Charulata | Reviewing documentation regularly | Assuming project requirements are clear | Participating in discussions and meetings , working wiith Figma | Scheduled a review session with team and meor to clarify project goals
2 | Sprint 2 | 2024-11-11 | 2024-11-22 | Vishal,Shambhavi,Prachi | Working on frontend and backend | Delaying review of tasks | Working on screens | Finished working with the screens
3 | Sprint 3 | 2024-11-25 | 2024-12-06 | Akriti,Paluru Sudeendra, Lakshi Sai Poojitha | Running both frontend and backend together | Delaying admin page | Asking for help when stuck | Completed backend & frontend with support from the team
4 | Sprint 4 | 2024-12-09 | 2024-12-20 | Mohammed Idrees,Kailash | Integrating frontend and backend and AI | Delaying voice input exploration | Working with Ollama | Completed AI integration
5 | Sprint 5 | 2024-12-23 | 2024-12-27 | Mohammed Idrees,Kailash | Running the whole project | Avoiding log in errors | Testing the working functionality | Completed voice input prototypes and received team feedback for improvements